## Start Here
Onboarding Tier & Cost Planner
What this tool is
Right-sizes onboarding to the property and prices the launch work. Not every property needs the luxury-estate treatment — but no tier drops the core controls.
How to use it
Section 1: rate each risk factor Low/Med/High. The tier equals the highest severity present (a small high-rise with biometric access and a tight window can be Full; a large simple home can be Standard).
Section 2: enter the hours for each launch task; the tool estimates onboarding cost and a per-turnover amortization so the work is recovered, not absorbed.
The rule
The highest-risk characteristic sets the tier — never square footage alone. Recover onboarding cost deliberately. Illustrative figures.

## Tier & Cost
ONBOARDING TIER & COST PLANNER
Chapter 5 · Property Onboarding · The STR Cleaning Blueprint™
The highest-risk characteristic sets the tier — not square footage or bedroom count. Rate each factor; the tier is the highest severity present. Then estimate and recover the onboarding cost.
1 · TIER ASSESSMENT
| Risk factor | Severity | Guidance
| Access complexity (locks, gates, restricted areas) |  |  | 0
| Linen resilience (PAR, laundry turnaround) |  |  | 0
| Amenity load (hot tub, pool, specialty systems) |  |  | 0
| Operating pressure (same-day turns, tight window) |  |  | 0
| Consequence of failure (luxury, VIP, owner, reviews) |  |  | 0
| Ownership / decision complexity (multi-owner, PM layers) |  |  | 0
| Travel / remoteness |  |  | 0
| Baseline condition / transition risk |  |  | 0
| Highest severity present | 0
| ASSIGNED ONBOARDING TIER | —
Assign an initial tier from pre-discovery signals, then confirm or raise it after the walkthrough. Regardless of tier, never drop the core controls: verified access, emergency contacts, responsibility boundaries, critical safety info, current instructions, and a readiness decision.
2 · ONBOARDING COST & RECOVERY
| Launch work | Hours | Notes
Pre-discovery research & scheduling
On-site walkthrough & discovery
Build the Property Knowledge Book
Photography & reference images
Team briefing / orientation
First-clean readiness review
Stabilization review (post-launch)
| Total launch labor-hours | 0
Burdened labor rate ($/hr)
Travel & mileage for onboarding
Materials (labels, supplies, printing)
| ESTIMATED ONBOARDING COST | 0
Recovery — amortize over how many turnovers?
Per-turnover add if amortized
Recover launch work deliberately — a separate onboarding fee, amortization across a defined number of turnovers, a priced initial reset, or a hybrid — and quote it in the proposal (Chapter 3) using the Chapter 4 method. Illustrative figures.

## Example — Lakeview
ONBOARDING TIER & COST PLANNER
Chapter 5 · Property Onboarding · The STR Cleaning Blueprint™ ¦ Summit — Lakeview Retreat
The highest-risk characteristic sets the tier — not square footage or bedroom count. Rate each factor; the tier is the highest severity present. Then estimate and recover the onboarding cost.
1 · TIER ASSESSMENT
| Risk factor | Severity | Guidance
| Access complexity (locks, gates, restricted areas) | High |  | 3
| Linen resilience (PAR, laundry turnaround) | Med |  | 2
| Amenity load (hot tub, pool, specialty systems) | High |  | 3
| Operating pressure (same-day turns, tight window) | Med |  | 2
| Consequence of failure (luxury, VIP, owner, reviews) | High |  | 3
| Ownership / decision complexity (multi-owner, PM layers) | Low |  | 1
| Travel / remoteness | Med |  | 2
| Baseline condition / transition risk | Med |  | 2
| Highest severity present | 3
| ASSIGNED ONBOARDING TIER | Full
Assign an initial tier from pre-discovery signals, then confirm or raise it after the walkthrough. Regardless of tier, never drop the core controls: verified access, emergency contacts, responsibility boundaries, critical safety info, current instructions, and a readiness decision.
2 · ONBOARDING COST & RECOVERY
| Launch work | Hours | Notes
| Pre-discovery research & scheduling | 1
| On-site walkthrough & discovery | 3
| Build the Property Knowledge Book | 2
| Photography & reference images | 1
| Team briefing / orientation | 1.5
| First-clean readiness review | 0.5
| Stabilization review (post-launch) | 1
| Total launch labor-hours | 10
| Burdened labor rate ($/hr) | 24.8
| Travel & mileage for onboarding | 25
| Materials (labels, supplies, printing) | 15
| ESTIMATED ONBOARDING COST | 288
| Recovery — amortize over how many turnovers? | 12
| Per-turnover add if amortized | 24
Recover launch work deliberately — a separate onboarding fee, amortization across a defined number of turnovers, a priced initial reset, or a hybrid — and quote it in the proposal (Chapter 3) using the Chapter 4 method. Illustrative figures.