Client Quality Review & 90-Day Implementation Plan

The STR Cleaning Blueprint™ · Chapter 7 · Operations Vault

Purpose.  Two tools that keep quality honest with clients and with yourself. The client review reports facts, not defensive conclusions — showing control instead of blame. The 90-day plan builds the quality system in a controlled sequence: define, then verify, then improve.

PART 1 — REPORT FACTS, NOT DEFENSIVE CONCLUSIONS

| Weak message | Professional quality communication |
| --- | --- |
| The last guests destroyed the place. | At arrival, the crew documented food debris throughout the kitchen, two stained duvet covers, and exterior trash requiring ~2.5 additional labor-hours. Photos attached. PM approved added service at 10:12 a.m.; revised completion 3:20 p.m. |
| The cleaner forgot the towels again. | The upstairs hall bath was released with two bath towels instead of the required four; corrected before check-in. Inventory count found the property below linen par; replenishment assigned for Monday. |
| Everything is fine now. | The entry lock battery was replaced and tested through three lock/unlock cycles at 2:08 p.m.; property released. Replacement interval will be reviewed — second low-battery event in 30 days. |

PART 2 — CLIENT QUALITY REVIEW FORM

| Property & period |  |
| --- | --- |
| Turnovers completed / inspected |  |
| Conditions found & standard referenced |  |
| Immediate action & operational impact |  |
| Client-dependent items (owner action) |  |
| Next owner / follow-up |  |

PROFESSIONAL STANDARD The cleaning company owns the quality of its work. It does not own every condition that affects the property. Professional reporting makes the boundary visible.

PART 3 — 90-DAY QUALITY SYSTEM IMPLEMENTATION PLAN

| First 30 days — DEFINE | Days 31–60 — VERIFY |
| --- | --- |
| • Write the company definition of guest-ready. • Identify non-negotiable company-wide standards. • Select highest-risk rooms & guest-impact conditions. • Convert vague instructions into observable standards. • Confirm current references; remove obsolete versions. • Define critical/major/minor/observation severity. | • Introduce a deliberate self-inspection routine. • Create risk-based supervisor inspection criteria. • Standardize essential completion & exception photos. • Calibrate supervisors & crew leads to one standard. • Record defects, corrections & rework in one system. • Begin tracking first-pass yield & repeat defects. |

Days 61–90 — IMPROVE

☐   Review the most frequent and costly defect categories.

☐   Complete root-cause analysis for repeat or high-consequence failures.

☐   Implement corrective actions with owners and due dates.

☐   Connect quality cost and inspection demand to Chapter 4 pricing.

☐   Publish a short quality dashboard; review with operations leaders.

☐   Recognize improved performance; update training from real findings.

IMPLEMENTATION RULE Build enough measurement to learn, then improve the system before adding more measurement.

A planning instrument, not a guarantee of business success. Vendor-neutral — usable with any tools, team structure, or software.  ·  The STR Cleaning Blueprint™

Client Quality Review & 90-Day Implementation Plan — Worked Example

The STR Cleaning Blueprint™ · Chapter 7 · Operations Vault ¦ Summit Cleaning Solutions

Worked for Summit Cleaning Solutions — a Lakeview Retreat arrival report to the owner, plus Summit's 90-day rollout as Emily formalized the quality system.

PART 1 — REPORT FACTS, NOT DEFENSIVE CONCLUSIONS

| Weak message | Professional quality communication |
| --- | --- |
| The last guests destroyed the place. | At arrival, the crew documented food debris throughout the kitchen, two stained duvet covers, and exterior trash requiring ~2.5 additional labor-hours. Photos attached. PM approved added service at 10:12 a.m.; revised completion 3:20 p.m. |
| The cleaner forgot the towels again. | The upstairs hall bath was released with two bath towels instead of the required four; corrected before check-in. Inventory count found the property below linen par; replenishment assigned for Monday. |
| Everything is fine now. | The entry lock battery was replaced and tested through three lock/unlock cycles at 2:08 p.m.; property released. Replacement interval will be reviewed — second low-battery event in 30 days. |

PART 2 — CLIENT QUALITY REVIEW FORM

| Property & period | Lakeview Retreat — July |
| --- | --- |
| Turnovers completed / inspected | 9 completed / 4 inspected |
| Conditions found & standard referenced | 1 minor (dim bulb) vs lighting standard — corrected |
| Immediate action & operational impact | Bulb replaced pre-arrival; no delay |
| Client-dependent items (owner action) | Linen below par — replacement approval requested |
| Next owner / follow-up | Owner to approve 2 duvet covers; Summit to restock |

PROFESSIONAL STANDARD The cleaning company owns the quality of its work. It does not own every condition that affects the property. Professional reporting makes the boundary visible.

PART 3 — 90-DAY QUALITY SYSTEM IMPLEMENTATION PLAN

| First 30 days — DEFINE | Days 31–60 — VERIFY |
| --- | --- |
| • Write the company definition of guest-ready. • Identify non-negotiable company-wide standards. • Select highest-risk rooms & guest-impact conditions. • Convert vague instructions into observable standards. • Confirm current references; remove obsolete versions. • Define critical/major/minor/observation severity. | • Introduce a deliberate self-inspection routine. • Create risk-based supervisor inspection criteria. • Standardize essential completion & exception photos. • Calibrate supervisors & crew leads to one standard. • Record defects, corrections & rework in one system. • Begin tracking first-pass yield & repeat defects. |

Days 61–90 — IMPROVE

☐   Review the most frequent and costly defect categories.

☐   Complete root-cause analysis for repeat or high-consequence failures.

☐   Implement corrective actions with owners and due dates.

☐   Connect quality cost and inspection demand to Chapter 4 pricing.

☐   Publish a short quality dashboard; review with operations leaders.

☐   Recognize improved performance; update training from real findings.

IMPLEMENTATION RULE Build enough measurement to learn, then improve the system before adding more measurement.

A planning instrument, not a guarantee of business success. Vendor-neutral — usable with any tools, team structure, or software.  ·  The STR Cleaning Blueprint™