PM Discovery Questionnaire & Portfolio Implementation Plan

The STR Cleaning Blueprint™ · Chapter 10 · Operations Vault

Purpose.  Discover the portfolio before onboarding the properties. Understand the systems, decision-makers, service promises, and exceptions first — then move through a disciplined sequence in which the launch date is earned by readiness, not set by enthusiasm.

PART 1 — DISCOVERY QUESTIONNAIRE

| Portfolio size, geography, property classes |  |
| --- | --- |
| Decision-makers & departments behind the manager |  |
| Reservation system (PMS) & connection type |  |
| Service promises to owners/guests we must uphold |  |
| Owner-by-owner exceptions & customization |  |
| Linen ownership & inspection expectations |  |
| Access methods & after-hours obligations |  |
| Billing entity, coding, terms, dispute handling |  |

PART 2 — IMPLEMENTATION SEQUENCE

| Stage | What professional judgment looks for | Status |
| --- | --- | --- |
| Discover | Portfolio, systems, decision-makers, promises, exceptions. |  |
| Design | Scope, responsibility, authority, information flow, economics, governance. |  |
| Configure | Property records, connections, pricing, contacts, checklists, billing. |  |
| Test | Deliberately test cancellation, access, approvals, escalation, invoicing. |  |
| Pilot | Representative properties under real conditions, controlled exposure. |  |
| Expand | Add volume only when capacity, quality, info, approvals, billing are stable. |  |

PART 3 — 90-DAY IMPLEMENTATION ROADMAP

| Period | Priority | Focus |
| --- | --- | --- |
| Days 1–30 — Define | Segment accounts; document decision-makers, scope, responsibility, sources of truth, approvals, pricing, payment, concentration. | Design the operating system |
| Days 31–60 — Control | Standardize discovery, readiness gates, pilots, issue handling, schedule reconciliation, extra-work evidence, account reporting. | Make it repeatable |
| Days 61–90 — Govern | Establish performance reviews, corrective partnership plans, account-profitability review, concentration safeguards, exit procedures. | Sustain and adapt |

A planning instrument, not a guarantee of business success. Vendor-neutral — usable with any tools, team structure, or software.  ·  The STR Cleaning Blueprint™

PM Discovery Questionnaire & Portfolio Implementation Plan — Worked Example

The STR Cleaning Blueprint™ · Chapter 10 · Operations Vault ¦ Summit Cleaning Solutions

Worked for Summit Cleaning Solutions — North Shore portfolio discovery led by Michelle Reyes with Sarah Mitchell, feeding a phased implementation.

PART 1 — DISCOVERY QUESTIONNAIRE

| Portfolio size, geography, property classes | 40 homes, lakeside corridor, 1–5 BR mix |
| --- | --- |
| Decision-makers & departments behind the manager | Sarah Mitchell (Ops); owners, reservations, maintenance, accounting |
| Reservation system (PMS) & connection type | PMS + iCal feed — update timing to confirm |
| Service promises to owners/guests we must uphold | Same-day readiness; owner-stay handling |
| Owner-by-owner exceptions & customization | Several; must be documented, not memorized |
| Linen ownership & inspection expectations | Mixed; some owner-supplied |
| Access methods & after-hours obligations | Smart locks + lockboxes; weekend coverage |
| Billing entity, coding, terms, dispute handling | Single AP; net-30 — negotiate |

PART 2 — IMPLEMENTATION SEQUENCE

| Stage | What professional judgment looks for | North Shore status |
| --- | --- | --- |
| Discover | Portfolio, systems, decision-makers, promises, exceptions. | Complete |
| Design | Scope, responsibility, authority, information flow, economics, governance. | In progress |
| Configure | Property records, connections, pricing, contacts, checklists, billing. | Building profiles |
| Test | Deliberately test cancellation, access, approvals, escalation, invoicing. | Scheduled |
| Pilot | Representative properties under real conditions, controlled exposure. | 5 homes selected |
| Expand | Add volume only when capacity, quality, info, approvals, billing are stable. | Gated on pilot |

PART 3 — 90-DAY IMPLEMENTATION ROADMAP

| Period | Priority | Focus |
| --- | --- | --- |
| Days 1–30 — Define | Segment accounts; document decision-makers, scope, responsibility, sources of truth, approvals, pricing, payment, concentration. | Design the operating system |
| Days 31–60 — Control | Standardize discovery, readiness gates, pilots, issue handling, schedule reconciliation, extra-work evidence, account reporting. | Make it repeatable |
| Days 61–90 — Govern | Establish performance reviews, corrective partnership plans, account-profitability review, concentration safeguards, exit procedures. | Sustain and adapt |

A planning instrument, not a guarantee of business success. Vendor-neutral — usable with any tools, team structure, or software.  ·  The STR Cleaning Blueprint™