Launch Readiness Gate & Pilot Property Selection

The STR Cleaning Blueprint™ · Chapter 10 · Operations Vault

Purpose.  The launch date must be earned by readiness. A blocking issue should prevent the affected property from launching; some items may be conditionally complete with a dated correction. And a pilot should not contain only the easiest homes — it should include the conditions most likely to expose weakness, while consequences remain controlled.

PART 1 — LAUNCH READINESS GATE

Green = ready. Yellow = conditional with a dated correction. A blocking (red) item stops that property from launching.

| Readiness item | Ready | Note | Flag |
| --- | --- | --- | --- |
| Agreement & economics |  |  |  |
| Signed agreement, scope, and price in place | ☐ |  |  |
| Implementation recovery & billing format agreed | ☐ |  |  |
| Information & schedule |  |  |  |
| Reservation connection live & mapped | ☐ |  |  |
| Cancellation & update-timing rule defined | ☐ |  | holiday fix |
| Source of truth named per data category | ☐ |  |  |
| Property & people |  |  |  |
| Property Profile complete for each home | ✔ |  | 1 pending |
| Access method verified per property | ☐ |  |  |
| Staffing & linen capacity confirmed for peak | ☐ |  |  |
| Decisions & issues |  |  |  |
| Approval thresholds & named backups set | ☐ |  |  |
| Escalation routes & issue classification set | ☐ |  |  |
| First invoice validated (mock run) | ☐ |  |  |

PART 2 — PILOT PROPERTY SELECTION (CHOOSE THE HARD CASES)

| Include a property that is… | Why | North Shore pick |
| --- | --- | --- |
| A large same-day turnover | Tests peak compression & capacity. |  |
| An owner-exception property | Tests documented customization. |  |
| A centralized-linen property | Tests linen routes & staging. |  |
| A remote route | Tests travel & timing. |  |
| A complex-access home | Tests access reliability. |  |

BLUEPRINT PRINCIPLE A successful pilot is not one in which nothing goes wrong. It is one in which the partnership detects, resolves, and learns from problems before full exposure begins.

A planning instrument, not a guarantee of business success. Vendor-neutral — usable with any tools, team structure, or software.  ·  The STR Cleaning Blueprint™

Launch Readiness Gate & Pilot Property Selection — Worked Example

The STR Cleaning Blueprint™ · Chapter 10 · Operations Vault ¦ Summit Cleaning Solutions

Worked for Summit Cleaning Solutions — North Shore launch gate and the deliberately hard 5-property pilot. One property failed because the owner-stay workflow never reached the cleaning schedule — the pilot did its job.

PART 1 — LAUNCH READINESS GATE

Green = ready. Yellow = conditional with a dated correction. A blocking (red) item stops that property from launching.

| Readiness item | Ready | Note | Flag |
| --- | --- | --- | --- |
| Agreement & economics |  |  |  |
| Signed agreement, scope, and price in place | ✔ |  |  |
| Implementation recovery & billing format agreed | ✔ |  |  |
| Information & schedule |  |  |  |
| Reservation connection live & mapped | ✔ |  |  |
| Cancellation & update-timing rule defined | ✔ |  | holiday fix |
| Source of truth named per data category | ✔ |  |  |
| Property & people |  |  |  |
| Property Profile complete for each home | ☐ |  | 1 pending |
| Access method verified per property | ✔ |  |  |
| Staffing & linen capacity confirmed for peak | ✔ |  |  |
| Decisions & issues |  |  |  |
| Approval thresholds & named backups set | ✔ |  |  |
| Escalation routes & issue classification set | ✔ |  |  |
| First invoice validated (mock run) | ✔ |  |  |

PART 2 — PILOT PROPERTY SELECTION (CHOOSE THE HARD CASES)

| Include a property that is… | Why | North Shore pick |
| --- | --- | --- |
| A large same-day turnover | Tests peak compression & capacity. | Lakeview 5BR — Sat |
| An owner-exception property | Tests documented customization. | Owner-stay home |
| A centralized-linen property | Tests linen routes & staging. | Central-linen condo |
| A remote route | Tests travel & timing. | North-end cabin |
| A complex-access home | Tests access reliability. | Smart-lock + gate |

BLUEPRINT PRINCIPLE A successful pilot is not one in which nothing goes wrong. It is one in which the partnership detects, resolves, and learns from problems before full exposure begins.

A planning instrument, not a guarantee of business success. Vendor-neutral — usable with any tools, team structure, or software.  ·  The STR Cleaning Blueprint™